## Sheet1
CHATFIELD RESERVOIR MITIGATION COMPANY
STATUS OF RECOMMENDATIONS OF THE PCT TECHNICAL ADVISORY COMMITTEE (TAC)
|  | Revision date: | 2020-02-03
Doc. No. | CRMC Recommendation |  | TAC Action |  |  | CRMC Action |  |  |  |  | PCT Action
| Date | Title | Date | Action | Notes | Date | Action | Notes | Posted on CRMC Website | Forward to PCT | Date | Action | Notes
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
001 | 2016-05-26 | Environmental Design Criteria | 2016-04-27 | 14 agree; 0 accept; 0 reject; 0 abstentions | Original action updated on 5/26/16 | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-06-13 | Sent to Colleen Horrihan using SAFE on 6-13-2016 | 2016-07-21 | Approved | None
002 | 2016-04-27 | EFU Credit - On-Site Habitat Preservation | 2016-04-27 | 13 agree; 0 accept; 0 reject; 1 abstain | Original action updated on 5/26/16. Clarified "as soon as practicable". | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-06-13 | Sent to Colleen Horrihan using SAFE on 6-13-2016 | 2016-07-21 | Approved | None
003 | 2016-05-26 | Tree Management | 2016-05-26 | 14 agree; 0 accept; 0 reject; 0 abstentions | Rejected debris screen; Include CPW as reviewer of TMP. | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-06-13 | Sent to Colleen Horrihan using SAFE on 6-13-2016 | 2016-07-21 | Approved | Keep Dam and Boater safety a priority. Include migratory birds and seasonal timing for tree removal in the Adaptive TMP
004 | 2016-05-26 | Gravel Pond - Pervious Dike | 2016-05-26 | 12 agree; 2 accept; 0 reject; 0 abstentions | Pervious berm not required | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-06-13 | Sent to Colleen Horrihan using SAFE on 6-13-2016 | 2016-07-21 | Approved | None
005 | 2016-06-30 | Borrow Area Refinement | 2016-07-08 | 12 agree; 0 accept; 0 reject; 0 abstentions | Refinement to borrow areas size and location is acceptable | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-07-19 | Sent to Colleen Horrihan using SAFE on 7-26-16 | 2016-08-18 | Approved, USACE members abstained | USACE still wants to see final earthwork
006 | 2016-06-30 | Evolution of On-site EM | 2016-07-08 | 15 agree; 0 accept; 0 reject; 0 abstentions | Titan Lake, Cigar Lake, Plum Creek refinements accepted. | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-07-19 | Sent to Colleen Horrihan using SAFE on 7-26-16 | 2016-08-18 | Approved, USACE members abstained | None
007 | 2016-08-15 | Deviation for Cut Low/Fill High | 2016-08-18 | 12 agree; 0 accept; 0 reject; 2 abstentions | USACE reps abstained since this is an Omaha level issue |  |  | No longer required since there is excess cut as of Jan 20 2017 | n/a
008 | 2016-10-17 | Joint Use Force Main | 2016-11-30 | 12 agree; 0 accept; 0 reject; 0 abstentions | Parks and CW&SD to complete an agreement | 2016-12-19 | Approved | Board accepted TAC recommendation | Yes | Sent to Colleen Horrihan using SAFE on 12-27-16 | 2017-01-30 | 3 USACE members abstained, 3 members approved | Comments from USACE on Dr Checks are being addressed. Plum Creek crossing to be designed by CW&SD
009 | 2017-01-12 | Bird EFUs | 2017-03-29 | 11 agree; 0 accept; 0 reject; 0 abstentions | None | 2017-04-03 | Approved | Board accepted TAC recommendation | Yes | Sent to Colleen Horrihan using SAFE on 4-18-17 | 2017-04-25 | Approved | None
010 | 2017-03-19 | Sugar Creek Phase 2 | 2017-10-19 | Unanimoud voice vote approval | Asphalt road will be 20ft wide, and a new culvert has been added to the parking area | 2017-10-25 | Approved | Board accepted design, with condition that significant changes would be brought back to the TAC and final draft would be approved by TAC | No |  | 2018-04-20 | Approved | None
011 | 2017-11-27 | South Platte River Environmental Mitigation | 2018-01-17 | 11 agree; 0 accept; 0 reject; 0 abstentions | Comments from TAC were accepted and incorporated | 2018-01-24 | Approved | Board accepted design, conditioned on an access plan for equiptment that is acceptable to USACE | No |  | 2018-05-25 | Approved | None
012 | 2018-03-01 | Plum Creek Plant Density | 2018-04-23 | No formal request for TAC action, but no concerns were shared. | No change in plant quantity in supplemental areas | 2018-04-05 | Approved | Board accepted new plant densities | No |  | 2018-05-25 | Approved | None
013 | 2018-04-09 | Marina Dredging Method | 2018-04-23 | 14 agree; 0 accept; 0 reject; 0 abstentions | Revised to describe all of the different variables needed | 2018-04-25 | Approved | Board accepted TAC recommendation | No |  | 2018-08-31 | Approved | None
014 | 2018-04-09 | On-site Mulch Disposal | 2018-04-23 | 11 agree; 1 accept; 0 reject; 0 abstentions | Would begin during Season 2 of construction | 2018-04-25 | Approved | Board accepted TAC recommendation | No |  |  | NOT APPROVED
015 | 2018-07-26 | Reservoir Monitoring & Modeling Report | 2018-07-26 | 8 agree; 0 accept; 0 reject; 0 abstentions | Combine monitoring and modeling reports for water quality. No rationale for 2 separate reports. |  |  | Does not require CRMC Board approval | N/A |  |  | No Approval Necessary
016 | 2018-07-26 | Marcy Gulch | 2018-09-17 | 8 agree; 0 accept; 0 reject; 0 abstentions | Approved, but recommended not moving forward with it |  |  | Does not require CRMC Board approval | N/A | Sent to Eric McKinney on 01-28-19 | 2019-03-12 | Approved | N/A
017 | 2018-05-21 | Mature Cottonwood Mitigation | 2018-09-17 | 9 agree; 0 accept; 0 reject; 0 abstentions | Compensatory mitigation for mature cottonwoods involves the creation and protection of ~43 acres of cottonwoods |  |  | Does not require CRMC Board approval | N/A | Sent to Eric McKinney on 5-14-19 | 2019-06-11 | Approved | None
018 | 2018-05-21 | Sandstone Ranch | 2018-09-17 | 9 agree; 0 accept; 0 reject; 1 abstentions | Will count as riparian conservation zone for Douglas County |  |  | Does not require CRMC Board approval | N/A
019 | 2018-09-06 | Schmidt Construction Property | 2018-10-22 | 12 agree; 0 accept; 0 reject; 0 abstentions | 4 parcels of land, making up 520 acres and accounting for ~32 EFUs |  |  | Does not require CRMC Board approval | N/A
020 | 2018-09-17 | EM 2 - FZ and Borrow Areas Revegetation Final Design | 2018-10-22 | 12 agree; 0 accept; 0 reject; 0 abstentions | Least amount of risk is for the plants to be placed at a higher elevation versus lower |  |  | Does not require CRMC Board approval | N/A | Sent to Eric McKinney on 5-13-19 | 2019-07-02 | Approved | None
021 | 2018-09-28 | FZ Vegetation Removal Plan | 2018-10-22 | 9 agree; 0 accept; 0 reject; 0 abstentions | Suggestion to have EFU assessment to make sure numbers are on track |  |  | Does not require CRMC Board approval | N/A | Sent to Colleen Horrihan on 9-28-18 | 2018-12-13 | Approved | None
022 | 2018-10-22 | Water Monitoring and Modeling Report Layout | 2018-12-17 | 11 agree; 0 accept; 0 reject; 0 abstentions | Report will be out earlier in the year (compared to original proposal) so actions can be taken as necessary |  |  | Does not require CRMC Board approval | N/A | Sent to Eric McKinney on 01-11-19 | 2019-02-22 | Approved | No ProjNet review necessary.
023 | 2018-12-17 | Adaptive Tree Management Plan (ATMP) | 2019-04-22 | 12 agree; 0 reject; 0 abstentions | Mainly reorganized information of previous versions. |  |  | Does not require CRMC Board approval | N/A | Sent to Eric McKinney on 5-29-19 | 2019-07-31 | Approved | None
024 | 2019-04-22 | 2018 Water Monitoring and Modeling Report | 2019-04-22 | 11 accept; 0 reject; 0 abstentions | No comments. |  |  | Does not require CRMC Board approval | N/A | Sent to Eric McKinney on 05-02-19 | 2019-06-11 | Approved | None
025 | 2019-04-22 | Compensatory Mitigation Monitoring Plan | 2019-04-22 | 10 accept; 0 reject; 1 abstention | Full approval pending regulating agency approval. |  |  | Does not require CRMC Board approval | N/A | Sent to Eric McKinney on 4-29-19 | 2019-07-02 | Approved | None
026 | 2019-11-19 | Schmidt and Sandstone Baseline Reports | 2019-11-19 | 9 accept; 0 reject; 0 abstention | Full appoval. |  |  | Does not require CRMC Board approval | N/A
027 | 2019-11-19 | EFU Monitoring Plan | 2019-11-19 | 9 accept; 0 reject; 0 abstention | Full approval. |  |  | Does not require CRMC Board approval | N/A | Sent to Eirc McKinney on 12/3/19 |  | Review in progress
028 | 2019-11-19 | Weeed Management Plan in FZ | 2019-11-19 | 9 accept; 0 reject; 0 abstention | Full approval. |  |  | Does not require CRMC Board approval | N/A | Sent to Eirc McKinney on 12-3-19 |  | Review in progress
Note on A27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Expanded BA5 and plans were put on hold for necessary revisions