## Sheet1
CHATFIELD RESERVOIR MITIGATION COMPANY | [9 empty] | Rev 16
STATUS OF RECOMMENDATIONS OF THE PCT TECHNICAL ADVISORY COMMITTEE (TAC)
|  | Revision date: | Monday, February 5, 2018
Doc. No. | CRMC Recommendation |  | TAC Action |  |  | CRMC Action |  |  |  |  | PCT Action
| Date | Title | Date | Action | Notes | Date | Action | Notes | Posted on CRMC Website | Forward to PCT | Date | Action | Notes
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
001 | 2016-05-26 | Environmental Design Criteria | 2016-04-27 | 14 agree; 0 accept; 0 agree | Original action updated on 5/26/16 | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-06-13 | Sent to Colleen Horrihan using SAFE on 6-13-2016 | 2016-07-21 | Approved | None
002 | 2016-04-27 | EFU Credit - On-Site Habitat Preservation | 2016-04-27 | 13 agree; 0 accept; 0 agree; 1 abstain | Original action updated on 5/26/16. Clarified "as soon as practicable". | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-06-13 | Sent to Colleen Horrihan using SAFE on 6-13-2016 | 2016-07-21 | Approved | None
003 | 2016-05-26 | Tree Management | 2016-05-26 | 14 agree; 0 accept; 0 agree | Rejected debris screen; Include CPW as reviewer of TMP. | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-06-13 | Sent to Colleen Horrihan using SAFE on 6-13-2016 | 2016-07-21 | Approved | Keep Dam and Boater safety a priority. Include migratory birds and seasonal timing for tree removal in the Adaptive TMP
004 | 2016-05-26 | Gravel Pond - Pervious Dike | 2016-05-26 | 12 agree; 2 accept; 0 reject | Pervious berm not required | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-06-13 | Sent to Colleen Horrihan using SAFE on 6-13-2016 | 2016-07-21 | Approved | None
005 | 2016-06-30 | Borrow Area Refinement | 2016-07-08 | 12 agree; 0 accept; 0 reject | Refinement to borrow aeas size and location is acceptable | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-07-19 | Sent to Colleen Horrihan using SAFE on 7-26-16 | 2016-08-18 | Approved, USACE members abstained | USACE still wants to see final earthwork
006 | 2016-06-30 | Evolution of On-site EM | 2016-07-08 | 15 agree; 0 accept; 0 reject | Titan Lake, Cigar Lake, Plum Creek refinements accepted. | 2016-07-25 | Approved | Board accepted TAC recommendation | 2016-07-19 | Sent to Colleen Horrihan using SAFE on 7-26-16 | 2016-08-18 | Approved, USACE members abstained | None
007 | 2016-08-15 | Deviation for Cut Low/Fill High | 2016-08-18 | 12 agree; 0 accept; 0 reject; 2 abstentions | USACE reps abstained since this is an Omaha level issue |  |  | No longer required since there is excess cut as of Jan 20 2017 | n/a
008 | 2016-10-17 | Joint Use Force Main | 2016-11-30 | 12 agree; 0 accept; 0 reject; 0 abstentions | Parks and CW&SD to complete an agreement | 2016-12-19 | Approved | Board accepted TAC recommendation |  | Sent to Colleen Horrihan using SAFE on 12-27-16 | 2017-01-30 | 3 USACE members abstained, 3 members approved | Comments from USACE on Dr Checks are being addressed. Plum Creek crossing to be designed by CW&SD
009 | 2017-01-12 | Bird EFUs | 2017-03-29 | 11 agree, 0 accept, 0 reject, 0 abstentions |  | 2017-04-03 | Approved | Board accepted TAC recommendation |  | Sent to Colleen Horrihan using SAFE on 4-18-17 | 2017-04-25 | Approved | None